## Summary
RTM status | Requirements
Verified | 30
Partial | 7
Failed | 6
Pending | 11
Total | 54
Verified = every linked test case passed. Failed = at least one linked test case failed. Partial = some passed, others not run. Pending = nothing run yet. Updated 26-Oct-2026.

## RTM
Req ID | Requirement | SRS / Design ref | Implemented in | Test case(s) | Test results | RTM status | Open defects | Comments
HMS-F-001 | The system shall allow a new user to register as a patient with name, email and password, and shall reject a duplicate email or invalid input. | 4.1 / SAD 3.4 | backend/controllers/authController.js; routes/authRoutes.js; middleware/authMiddleware.js (auth + RBAC); frontend/src/context/AuthContext.jsx | TC-Auth-01, TC-Auth-02, TC-Auth-03 | TC-Auth-01: Pass; TC-Auth-02: Pass; TC-Auth-03: Pass | Verified
HMS-F-002 | The system shall authenticate users by email and password and issue a JWT containing user id, role and expiry time. | 4.1 / SAD 3.4 | backend/controllers/authController.js; routes/authRoutes.js; middleware/authMiddleware.js (auth + RBAC); frontend/src/context/AuthContext.jsx | TC-Auth-04, TC-Auth-08 | TC-Auth-04: Pass; TC-Auth-08: Pass | Verified
HMS-F-003 | The system shall show a generic error for invalid credentials and shall not reveal whether the email or the password was wrong. | 4.1 / SAD 3.4 | backend/controllers/authController.js; routes/authRoutes.js; middleware/authMiddleware.js (auth + RBAC); frontend/src/context/AuthContext.jsx | TC-Auth-05, TC-Auth-06 | TC-Auth-05: Pass; TC-Auth-06: Pass | Verified
HMS-F-004 | The system shall allow each protected function only to its permitted roles (Patient, Doctor, Administrator), returning 401 without a valid token and 403 for a wrong role. | 4.1 / SAD 3.4 | backend/controllers/authController.js; routes/authRoutes.js; middleware/authMiddleware.js (auth + RBAC); frontend/src/context/AuthContext.jsx | TC-Auth-07, TC-Auth-09, TC-E2E-04 | TC-Auth-07: Pass; TC-Auth-09: Pass; TC-E2E-04: Not run | Partial
HMS-F-005 | The system shall allow a logged-in user to log out, ending the session on the client. | 4.1 / SAD 3.4 | backend/controllers/authController.js; routes/authRoutes.js; middleware/authMiddleware.js (auth + RBAC); frontend/src/context/AuthContext.jsx | TC-Auth-10 | TC-Auth-10: Not run | Pending |  | Logout is frontend only: token is removed in the browser. No server-side logout; token stays valid until expiry. TC-Auth-10 needs a UI run.
HMS-F-006 | The system shall refuse login for deactivated accounts. | 4.1 / SAD 3.4 | backend/controllers/authController.js; routes/authRoutes.js; middleware/authMiddleware.js (auth + RBAC); frontend/src/context/AuthContext.jsx | TC-Auth-12 | TC-Auth-12: Pass | Verified
HMS-F-010 | The system shall maintain a patient profile (name, date of birth, gender, phone, address) that the patient can view. | 4.2 / SAD 3.4 | backend/controllers/patientController.js; routes/patientRoutes.js | TC-Pat-01 | TC-Pat-01: Pass | Verified
HMS-F-011 | The system shall allow a patient to update permitted profile fields; role and identifiers cannot be changed. | 4.2 / SAD 3.4 | backend/controllers/patientController.js; routes/patientRoutes.js | TC-Pat-02, TC-Pat-03 | TC-Pat-02: Pass; TC-Pat-03: Pass | Verified
HMS-F-012 | The system shall validate profile input (for example phone format, date of birth not in the future) and return clear messages. | 4.2 / SAD 3.4 | backend/controllers/patientController.js; routes/patientRoutes.js | TC-Pat-04 | TC-Pat-04: Fail | Failed | #17 | Phone format and future date of birth are not validated.
HMS-F-013 | The system shall deny a patient access to any other patient's information. | 4.2 / SAD 3.4 | backend/controllers/patientController.js; routes/patientRoutes.js | TC-Pat-05 | TC-Pat-05: Pass | Verified
HMS-F-014 | The system shall let a doctor view the profile of a patient who has an appointment with that doctor, and an administrator view any patient profile. | 4.2 / SAD 3.4 | backend/controllers/patientController.js; routes/patientRoutes.js | TC-Pat-06, TC-Pat-07 | TC-Pat-06: Fail; TC-Pat-07: Fail | Failed | #18 | SRS expects doctor and admin access; all patient routes are patient-only.
HMS-F-020 | The system shall maintain a doctor profile (name, specialization, contact details); doctor accounts are created by an administrator. | 4.3 / SAD 3.4 | backend/controllers/doctorController.js; routes/doctorRoutes.js; adminController.js (create doctor) | TC-Doc-01 | TC-Doc-01: Not run | Pending |  | Admin creation tested (TC-Adm-05); login of the new doctor needs a real database run (TC-Doc-01).
HMS-F-021 | The system shall allow a doctor to add and remove availability slots (date, start time, end time) in 30-minute units. | 4.3 / SAD 3.4 | backend/controllers/doctorController.js; routes/doctorRoutes.js; adminController.js (create doctor) | TC-Doc-02, TC-Doc-06 | TC-Doc-02: Pass; TC-Doc-06: Pass | Verified
HMS-F-022 | The system shall reject availability slots that overlap an existing slot of the same doctor. | 4.3 / SAD 3.4 | backend/controllers/doctorController.js; routes/doctorRoutes.js; adminController.js (create doctor) | TC-Doc-03 | TC-Doc-03: Pass | Verified
HMS-F-023 | The system shall allow a patient to search doctors by name or specialization. | 4.3 / SAD 3.4 | backend/controllers/doctorController.js; routes/doctorRoutes.js; adminController.js (create doctor) | TC-Doc-04 | TC-Doc-04: Pass | Verified
HMS-F-024 | The system shall show a patient the free slots of a doctor and shall not show booked slots as free. | 4.3 / SAD 3.4 | backend/controllers/doctorController.js; routes/doctorRoutes.js; adminController.js (create doctor) | TC-Doc-05 | TC-Doc-05: Pass | Verified
HMS-F-030 | The system shall allow a patient to book a free slot with a doctor after checking availability, and set the status to Confirmed. | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-01, TC-E2E-01 | TC-Apt-01: Pass; TC-E2E-01: Not run | Partial |  | Status is Scheduled in code; SRS and test sheet say Confirmed. TC-E2E-01 not run.
HMS-F-031 | The system shall ensure a slot has at most one active appointment, even when two requests arrive at the same time. | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-02, TC-Apt-03, TC-Int-01 | TC-Apt-02: Pass; TC-Apt-03: Not run; TC-Int-01: Not run | Partial |  | Locking and 409 logic tested with a mocked DB. Concurrent booking (TC-Apt-03) and TC-Int-01 need a real MySQL run.
HMS-F-032 | The system shall reject bookings in the past or for a non-existent doctor. | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-04, TC-Apt-05 | TC-Apt-04: Fail; TC-Apt-05: Pass | Failed | #19 | Past dates are accepted.
HMS-F-033 | The system shall let a patient view their own appointments and a doctor view their own appointments. | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-06, TC-Apt-07 | TC-Apt-06: Pass; TC-Apt-07: Pass | Verified
HMS-F-034 | The system shall allow a patient to reschedule an appointment to another free slot and free the old slot. | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-08, TC-Apt-09 | TC-Apt-08: Pass; TC-Apt-09: Pass | Verified
HMS-F-035 | The system shall allow a patient to cancel an appointment and shall maintain its status (Confirmed, Cancelled, Completed); a cancelled slot becomes free. | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-10 | TC-Apt-10: Pass | Verified
HMS-F-036 | The system shall allow a user to modify only their own appointments (administrator excepted). | 4.4 / SAD 3.4 | backend/controllers/appointmentController.js; routes/appointmentRoutes.js | TC-Apt-11 | TC-Apt-11: Pass | Verified |  | API returns 404, not the 403 in the SRS. Nothing is modified, so the outcome is safe.
HMS-F-040 | The system shall allow a doctor to create a medical record (diagnosis, notes) for a patient who has an appointment with that doctor. | 4.5 / SAD 3.4 | backend/controllers/medicalRecordController.js; routes/medicalRecordRoutes.js | TC-Rec-01, TC-E2E-02 | TC-Rec-01: Pass; TC-E2E-02: Not run | Partial
HMS-F-041 | The system shall allow a doctor to retrieve and update the medical records of their patients and shall store the update time. | 4.5 / SAD 3.4 | backend/controllers/medicalRecordController.js; routes/medicalRecordRoutes.js | TC-Rec-02, TC-Rec-03 | TC-Rec-02: Pass; TC-Rec-03: Pass | Verified
HMS-F-042 | The system shall allow a patient to view their own medical records but not create or edit them. | 4.5 / SAD 3.4 | backend/controllers/medicalRecordController.js; routes/medicalRecordRoutes.js | TC-Rec-05, TC-Rec-06 | TC-Rec-05: Pass; TC-Rec-06: Pass | Verified
HMS-F-043 | The system shall deny access to a patient's medical records for any unauthorized user. | 4.5 / SAD 3.4 | backend/controllers/medicalRecordController.js; routes/medicalRecordRoutes.js | TC-Rec-04, TC-Rec-05 | TC-Rec-04: Fail; TC-Rec-05: Pass | Failed | #20 | Doctor without an appointment gets an empty 200, not 403. No data leaks.
HMS-F-044 | The system shall validate required fields (patient, doctor, diagnosis) before saving a record. | 4.5 / SAD 3.4 | backend/controllers/medicalRecordController.js; routes/medicalRecordRoutes.js | TC-Rec-07 | TC-Rec-07: Pass | Verified
HMS-F-050 | The system shall restrict all administrative functions to the Administrator role. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-01, TC-Adm-02 | TC-Adm-01: Not run; TC-Adm-02: Pass | Partial |  | Dashboard (TC-Adm-01) needs a UI run.
HMS-F-051 | The system shall let an administrator list and view users, patients and doctors, without returning any password data. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-03, TC-Adm-04 | TC-Adm-03: Fail; TC-Adm-04: Pass | Failed | #22 | Role filter missing.
HMS-F-052 | The system shall let an administrator create doctor accounts and patient accounts. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-05, TC-Doc-01, TC-E2E-03 | TC-Adm-05: Pass; TC-Doc-01: Not run; TC-E2E-03: Not run | Partial
HMS-F-053 | The system shall let an administrator deactivate and reactivate user accounts. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-06, TC-Adm-07 | TC-Adm-06: Pass; TC-Adm-07: Pass | Verified
HMS-F-054 | The system shall let an administrator view all appointments with filters and cancel or change the status of an appointment. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-08, TC-Adm-09, TC-E2E-03 | TC-Adm-08: Fail; TC-Adm-09: Pass; TC-E2E-03: Not run | Failed | #22 | Doctor, patient, date and status filters missing.
HMS-F-055 | The system shall show an administrator an overview of counts of patients, doctors and appointments. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-10 | TC-Adm-10: Pass | Verified
HMS-F-056 | The system shall record authentication events and administrative actions in an audit log that an administrator can view. | 4.6 / SAD 3.4 | backend/controllers/adminController.js; routes/adminRoutes.js; services/auditLogger.js | TC-Adm-11, TC-Auth-11 | TC-Adm-11: Pass; TC-Auth-11: Pass | Verified
HMS-F-060 | The system shall store users, patients, doctors, availability, appointments and medical records in a MySQL database that keeps data across application restarts. | 4.7 / SAD 3.4 | database/schema.sql; backend/db.js; appointmentController.js (transactions) | TC-DB-01 | TC-DB-01: Not run | Pending |  | Needs a real database run.
HMS-F-061 | The system shall enforce referential integrity between related records. | 4.7 / SAD 3.4 | database/schema.sql; backend/db.js; appointmentController.js (transactions) | TC-DB-02 | TC-DB-02: Not run | Pending |  | Needs a real database run (foreign keys).
HMS-F-062 | The system shall complete operations that change several records (for example booking) fully or not at all. | 4.7 / SAD 3.4 | database/schema.sql; backend/db.js; appointmentController.js (transactions) | TC-DB-03 | TC-DB-03: Pass | Verified |  | Rollback verified with a mocked connection; real database run pending.
HMS-F-063 | The system shall support backup and restore of the database. | 4.7 / SAD 3.4 | database/schema.sql; backend/db.js; appointmentController.js (transactions) | TC-DB-04 | TC-DB-04: Not run | Pending |  | Manual backup and restore not done.
HMS-NF-001 | Performance | 5 / SAD 3.1 Goals | appointmentController.js, doctorController.js, db.js (connection pool) | TC-Perf-01 | TC-Perf-01: Not run | Pending |  | Load test pending (issue #16).
HMS-NF-002 | Reliability | 5 / SAD 4.4 Error Handling | backend/app.js (error handler, JSON limit); all controllers | TC-Rel-01 | TC-Rel-01: Pass | Verified |  | Malformed JSON and database error verified. Oversized body returns 500, should be 413 (#21).
HMS-NF-003 | Usability | 5 / SAD 4.5 UX Design | frontend/src/pages | TC-UX-01 | TC-UX-01: Not run | Pending |  | Timed walkthrough pending (issue #16).
HMS-NF-004 | Maintainability | 5 / SAD 3.5 Layered Architecture | .github/workflows/ci.yml; backend eslint + jest; layered routes/controllers/services | TC-Maint-01 | TC-Maint-01: Not run | Pending |  | CI workflow exists (lint + test). Failing-PR check (TC-Maint-01) not run.
HMS-NF-005 | Data integrity | 5 / SAD 3.1 Goals | database/schema.sql; appointmentController.js (row locking, transactions) | TC-Int-01 | TC-Int-01: Not run | Pending
HMS-NF-006 | Compatibility | 5 / SAD 3.6 Technology Stack | frontend (React + CSS) | TC-Compat-01 | TC-Compat-01: Not run | Pending |  | Browser and 360 px tests pending (issue #16).
HMS-NF-007 | Auditability | 5 / SAD 4.4.2 Logging | services/auditLogger.js; middleware/auditMiddleware.js; authRoutes; adminRoutes | TC-Aud-01 | TC-Aud-01: Pass | Verified |  | Auth events logged via authRoutes, admin actions via adminRoutes; SRS RTM lists only Admin Service.
HMS-SR-001 | Password hashing | 5.1.2 / SAD 3.9 Password Security | authController.js (bcrypt) | TC-Sec-01, TC-Sec-03 | TC-Sec-01: Pass; TC-Sec-03: Pass | Verified |  | Hash on write verified with a mocked DB; direct table inspection not done.
HMS-SR-002 | JWT signing and expiry | 5.1.2 / SAD 3.9 Authentication | config/env.js; middleware/authMiddleware.js (JWT verify, DB role check) | TC-Sec-02, TC-Auth-08 | TC-Sec-02: Pass; TC-Auth-08: Pass | Verified
HMS-SR-003 | Server-side RBAC | 5.1.2 / SAD 3.9 Authorization | middleware/authMiddleware.js (authorize); every route file | TC-Sec-04 | TC-Sec-04: Pass | Verified
HMS-SR-004 | Input validation | 5.1.2 / SAD 3.9 Input Validation | express-validator in routes; parameterised queries in controllers | TC-Sec-05, TC-Sec-06 | TC-Sec-05: Pass; TC-Sec-06: Not run | Partial |  | Injection payloads handled. Script-tag display test (TC-Sec-06) needs a browser.
HMS-SR-005 | HTTPS and CORS | 5.1.2 / SAD 3.9 Data Protection | backend/app.js (CORS, helmet) | TC-Sec-08 | TC-Sec-08: Not run | Pending |  | CORS and headers verified. HTTPS/TLS is not documented anywhere in the repo.
HMS-SR-006 | Secret handling | 5.1.2 / SAD 3.9 Database Security | .gitignore; backend/.env.example; config/env.js | TC-Sec-07 | TC-Sec-07: Pass | Verified
HMS-SR-007 | No sensitive data in logs | 5.1.2 / SAD 4.4.1 Error Handling | backend/app.js (error handler); services/auditLogger.js | TC-Sec-03, TC-Sec-09 | TC-Sec-03: Pass; TC-Sec-09: Pass | Verified
HMS-SR-008 | Audit logging | 5.1.2 / SAD 3.9 Audit and Logging | services/auditLogger.js; middleware/auditMiddleware.js | TC-Aud-01, TC-Adm-11 | TC-Aud-01: Pass; TC-Adm-11: Pass | Verified

## Inconsistencies
# | Where | Issue | Suggested fix | Owner
1 | SRS section 8 RTM | Status column uses N/P/A but the legend is never defined, and all 54 rows still say N | Define the legend or use the Status in RTM_HMS.xlsx; update all rows | Rolla (SRS) with Rohan
2 | SRS section 6 / 8 exit criteria | Exit criteria say the RTM shows all test cases passed. 7 test cases currently fail and 18 are not run | Fix defects #17 to #22 and run the remaining cases before sign-off | All
3 | HMS-F-030 / TC-Apt-01 | SRS and test sheet say status "Confirmed"; code and database use "Scheduled" | Change SRS and test sheet to "Scheduled", or change the code | Amulya
4 | HMS-F-036 / TC-Apt-11 | Expected 403, API returns 404 for another patient's appointment | Accept 404 and update the expected result | Rohan
5 | HMS-F-014 / TC-Pat-06, 07 | SRS requires doctor and admin to view patient profiles; code is patient-only (#18) | Fix the code | Rolla
6 | HMS-F-043 / TC-Rec-04 | Expected 403, actual empty 200 (#20) | Fix the code or change the SRS to say empty result | Krishna
7 | HMS-F-051, HMS-F-054 | List filters in the SRS are not implemented (#22) | Implement the filters | Rohan
8 | HMS-NF-007 | SRS RTM lists only Admin Service, but login events are logged by the auth routes | Add Authentication Service to the module column | Rolla / Rohan
9 | STP section 5 | Says integration tests run against a MySQL test schema; the Jest suite uses a mocked database and CI has no MySQL service, so TC-DB-01, DB-02, Apt-03 and Int-01 are not automated | Add a MySQL service to the CI workflow, or state in the STP that these are manual | Rohan
10 | STP section 8 | Lists a Postman collection as a deliverable; none found in the repo | Add the collection or remove it from the STP | Rohan
11 | HMS-F-005 Logout | No server-side logout. Token stays valid until expiry | Document as a design decision in the SAD | Amulya
12 | HMS-SR-005 | No HTTPS/TLS note anywhere in the repo | Add a deployment note to the SAD or README | Amulya
13 | HMS-NF-001, 003, 006 | Load, usability and browser tests not done yet (issue #16) | Run in issue #16 | Rohan